## Sheet1
Times in hours | Sprint 1 Task Time Requirements Est. |  | Sprint 1 Task Time Actual Requirements |  | Sprint 2 Task Time Requirements Est. |  | Sprint 2 Task Time Actual Requirements |  | Sprint 3 Task Time Requirements Est. |  | Sprint 3 Task Time Actual Requirements |  | Sprint 4 Task Time Requirements Est. |  | Sprint 4 Task Time Actual Requirements
| Week 1 |  | Week 1 |  | Week 1 |  | Week 1 |  | Week 1 |  | Week 1 |  | Week 1 |  | Week 1
Backend | 0 | Backend | 0 | Backend | 5 | Backend | 2.5 | Backend |  | Backend |  | Backend |  | Backend
Frontend | 0 | Frontend | 0 | Frontend | 6 | Frontend |  | Frontend |  | Frontend |  | Frontend |  | Frontend
Documentation | 0.75 | Documentation | 1 | Documentation | 0.375 | Documentation |  | Documentation |  | Documentation |  | Documentation |  | Documentation
Total | 0.75 | Total | 1 | Total | 11.375 | Total | 2.5 | Total | 0 | Total | 0 | Total | 0 | Total | 0
| Week 2 |  | Week 2 |  | Week 2 |  | Week 2 |  | Week 2 |  | Week 2 |  | Week 2 |  | Week 2
Backend | 6 | Backend | 5 | Backend | 4 | Backend | 0.25 | Backend |  | Backend |  | Backend |  | Backend
Frontend |  | Frontend |  | Frontend | 7 | Frontend |  | Frontend |  | Frontend |  | Frontend |  | Frontend
Documentation |  | Documentation |  | Documentation | 0.375 | Documentation |  | Documentation |  | Documentation |  | Documentation |  | Documentation
Total | 6 | Total | 5 | Total | 11.375 | Total | 0.25 | Total | 0 | Total | 0 | Total | 0 | Total | 0
[9 empty] | Week Number | Estimates | Actual
[9 empty] | 1 | 0.75 | 1
[9 empty] | 2 | 6 | 5
[9 empty] | 3 | 11.375 | 2.5
[9 empty] | 4 | 11.375 | 0.25
[9 empty] | 5 | 0 | 0
[9 empty] | 6 | 0 | 0
[9 empty] | 7 | 0 | 0
[9 empty] | 8 | 0 | 0
[9 empty] | 1 | 29.5 | 8.75
[9 empty] | 2 | 28.75 | 7.75
[9 empty] | 3 | 22.75 | 2.75
[9 empty] | 4 | 11.375 | 0.25
[9 empty] | 5 | 0 | 0
[9 empty] | 6 | 0 | 0
[9 empty] | 7 | 0 | 0
[9 empty] | 8 | 0 | 0