## Sheet1
Task Number | Tasks for Finished Project (~chronological) | Time Est. | Time Actual | ∆ | Key
| Research API usage and access necessary keys | 1 | 1 | 0 | Backend
| Create folders/files for containing the relevant documentation for the project | 1 | 2 | 1 | Frontend
| Set up github with at least 3 branches - main, dev, frontend | 1 | 0.5 | -0.5 | Documentation
| Set up excel SS for the burndown data and chart - time-based bd chart | 1 | 1.5 | 0.5
| Create basic strucutre of website (wireframe) |  |  | 0
| Create a DBS, Provide access to all team members |  |  | 0
| Python script for scraping data (basic) |  |  | 0
| Python script for scraping data (error handling and integration with database manipulation script (functions) |  |  | 0
| Database creation, manipulation scripts |  |  | 0
| Database query script |  |  | 0
| Basic flask application to serve data to frontend | 2 | 1.5 | -0.5
| Research crontab |  |  | 0
| Map integration and initial UI design |  |  | 0
| Designing frontened in html/css |  |  | 0
| Create README, basic flowchart |  |  | 0
| Write SQL queries |  |  | 0
| Restructure database access functions |  |  | 0
| Create database table for weather information |  |  | 0
| Test recovery of information from DB |  |  | 0
| Refine stations table |  |  | 0
| Create JSON backup |  |  | 0
| Create ER diagram for DBS tables |  |  | 0
| ML Research - model |  |  | 0
| ML Research - code |  |  | 0
| ML model generation |  |  | 0
| ML model graphs added to frontend |  |  | 0
| Map functionality, visuals |  |  | 0
| Map functionality, visuals |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Sprint Number | Task allocation by sprint (sprint backlog) |  |  | 0
1 | Research API usage and access necessary keys |  |  | 0
| Create folders/files for containing the relevant documentation for the project |  |  | 0
| Set up github with at least 3 branches - main, dev, frontend |  |  | 0
| Set up excel SS for the burndown data and chart - time-based bd chart |  |  | 0
| Create basic strucutre of website (wireframe) |  |  | 0
| Create a DBS, Provide access to all team members |  |  | 0
| Python script for scraping data (basic) |  |  | 0
| Database creation, manipulation scripts |  |  | 0
0
2 | Database query script |  |  | 0
| Basic flask application to serve data to frontend |  |  | 0
| Research crontab |  |  | 0
| Map integration and initial UI design |  |  | 0
| Designing frontened in html/css |  |  | 0
| Create README, basic flowchart |  |  | 0
| Python script for scraping data (error handling and integration with database manipulation script (functions) |  |  | 0
| Write SQL queries |  |  | 0
| Restructure database access functions |  |  | 0
| Create database table for weather information |  |  | 0
| Test recovery of information from DB |  |  | 0
0
3 | ML Research - model |  |  | 0
| ML Research - code |  |  | 0
0
0
0
0
0
0
0
4 | Create ER diagram for DBS tables |  |  | 0